## Sheet1
Project Checklist Project Name Page 1
Date Project Manager:
Pre-construction meeting (Internal) Upper Mgt Accounting Estimating
Pre-construction Meet with Client
Offsite Considerations Local Regs Building permit Obtain Get to know building inspectors Business License Any ordinances that will affect project Any potential political problems Adjacent Properties Neighbors/Adjacent property Introduce yourself to neighbors Point out inconveniences to them Local Availability Suppliers Subs Equipment Employees Off-site logistics Travel Equipment Repair/Maintenance
Onsite Considerations Soil types and subsurface conditions Onsite Logistics Ingress/Egress Equipment Limitations
Schedule Preparation Tasks Lead/Lag Time Time to complete Predecessor Relationships Resources Internal Review
Meeting with Suppliers/Subs
Schedule to: Client, Subs, Employees
Contracts and PO’s PO’s (Separate by delivery) Subcontracts Equipment PO’s (rentals)/Requests (in-house equipment)
Temporary Facilities

## Sheet2
Project Checklist Project Name Page 2
Date Project Manager:
Construction Trailer Portable Toilets Temporary Power Phones/Fax Fencing Trash
Signs Project Description Sign Directions for deliveries Warning signs
Items needed at the Jobsite Plans & Specs Forms (W-2’s, Timecards, PO’s, Change Orders, Inspection) Project Manual Budget Most Recent Job Cost Reports Copy of the contract Schedule (Updated regularly & Hopefully by the project manager) Company Policies & Procedures Company phone list Contact list (Subs, Suppliers, Inspectors, Architects, Engineers)
Post Construction Meeting (Upper Mgt, Field Mgt, Estimator, Accounting)